## Sheet1
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Project Brief
Background Research
Write up
Project Plan
Time allocation
Formal Gantt Chart
Research
Research and begin learning Scyther
Literature review
Design
Establish Formal Criteria for my polices
Compose a list of policies
Evaluate policies against criteria
Approach
Produce policies and standards that are to be evaluated in Scyther
Progress report
Write up
Build
Model Policies in scyther
Modfiy policies based on Scyther results
Testing
Final report
A clear statement of the problem and goals of the project
Review of background literature
An analysis and specification of the policies I have chosen
A detailed design
Scyther Implementation
Scyther Evaluation process
A critical evaluation of my project
Conclusions and future work
References to the literature
Appendices providing Scyther policies and technical references
Project viva